**DISASTER RISK REDUCTION WEEKLY REPORT.**

WEEK**: From:**  10th March, 2025 **To:** 16th March, 2025

1. EXECUTIVE SUMMARY

|  |
| --- |
| Several fire incidences were experienced during the week as various sub counties embarked on Hazard mapping activities. |

2. KEY UPDATES AND ACTIVITIES

|  |  |
| --- | --- |
| Incidences responded to | 05 no of Fire incidents  02 no of Flooding incidents |
| Community engagement forums | 03 |
| Stakeholder engagement | 03 Ruaraka  Kibra  Kamukunji |
|  |  |

3. ONGOING ACTIVITIES

|  |
| --- |
| Hazard mapping in all 17 sub counties |
| Community engagement programs |
|  |

4. UPCOMING ACTIVITIES

|  |  |
| --- | --- |
| Hazard mapping | 17 Sub counties |
| Community engagement | 06 Sub counties |
|  |  |

5. CHALLENGES.

|  |
| --- |
| * Facilitation * Mobility across the sub counties * Insecurity * Accessibility |

6. CONCLUSION.

|  |
| --- |
| The ongoing Hazard mapping activities are aimed at coming up with preparedness and mitigation measures to the identified hazards. |